## Sheet1
Date | Atendees | Project Updates | Next Week Goals | Task Assignments
2013-04-28 | Prashanth | ● Prashanth: Recreated UML diagrams on paper, models and architecture (service still needs to be done). Completed AngularJS tutorial. ● Sravan: Studies GIT first 2 chapters, Angular JS tutorial. | Divide the project into manageable pieces. Claim ownership of these pieces and begin working | Prashanth: Divide the project. Begin working on one of the parts, Continue AngularJS training.
2013-05-05 | Prashanth. Sravan: AWOL | ● Prashanth: Billrive Svc basic controllers, associated service method skeletons, Basic Domain objects created. Uploaded to Github repository ● Sravan: | Continue developing backend till we have all basic services up. Then we can focus on the client application and then finally move to DAO | ● Prashanth: Continue developing backend. Need to complete asap. Also try to create a basic seed structure for client ● Sravan: Study the services,ctrls created this week. Get an understanding of the overall architecture and pick the modules which you would like to start working on this week.
2013-05-12 | Prashanth | ● Prashanth: Changes to svc. Converted LinkedLists to Arraylists with proper init. Improved Bill data model. Svc now generates sufficient json data that the UI can list the bills to the user. ● Sravan: | Create basic angular seed structure. The skeleton should pave the way being able to aggresively begin development on billrive-client app | ● Prashanth: Separate out all the elements like directives, modules, controllers, services, filters. Begin creating a Bills page to list the bills with Angular JS. ● Sravan: Study Bill data model, Improve the model based on the Mocks. Next head to Groups and Friends. Begin modelling them as well.
2013-05-19 | Prashanth, Sravan | ● Prashanth: Created seed with clear strcuture, created bill partial page, used bootstrap to generate clean output. Was able to understand and use modules, controllers, services, factories etc. of Angular JS ● Sravan: Looked into wiremocks to understand the requirements. Understood basic flow of application | Create basic angular seed structure. The skeleton should pave the way being able to aggresively begin development on billrive-client app | ● Prashanth: Create Angular JS Service. Add bill retrevial calls through GET method. Feed dynamic bill data to UI. Implement Edit, Delete basic screens. ● Sravan: Task 1: Study the two chapters relating to Spring IoC initialization, controls. Task 2: Understand various annotations used in spring, their meanings. Differenciate between @Service, @Autowired etc. Task 3: Fix /rest/2/bills /rest/3/bills as they should give different json. Currently now matter what the id, the controller returns the same output.
2013-05-26 | Prashanth. Sravan: | ● Prashanth: Implemented service call to retreive JSON. Had to add CORS filters to avoid cross site blocking. Still need to implement basic Edit, Delete Screens ● Sravan: | Continue developing backend till we have all basic services up. Then we can focus on the client application and then finally move to DAO | ● Prashanth: Continue building bills creen ● Sravan: Enhance Bills backend domain objects.
2013-06-02 | Prashanth. Sravan: | ● Prashanth: Consumed Server generated JSON and displayed them as a simple bootstrap list. created basic angular project. Explored bower, grunt. ● Sravan: Studied the two chapters related to spring ioc. Understood annotations. Able to follow the structure and flow of the application. | Continue developing backend till we have all basic services up. Then we can focus on the client application and then finally move to DAO | ● Prashanth: Continue building bills creen ● Sravan: Enhance Bills backend domain objects.
2013-06-09 | Prashanth,Sravan, Karthik | ● Prashanth: Created a whole new UI layout from scratch with Bootstrap CSS/JS. Created a AddBill page. Reorganized controllers, services to reflect the changes. Hardcoded JSON in services to support addBill features. Wrote methods to support group switching in addbill. Created a simple bill calculation page and the corresponding UI elements and navigation. ● Sravan: Added group service method Analysed the service method requirements. | Complete AddBill (Simple, Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. Add MySQL driver to Application server. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). Complete Group service methods. | ● Prashanth: Complete AddBill (Simple, Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. ● Karthik: Install IDE, Glassfish. Setup basic dev environment. Clone repo. Study service & client. Add MySQL driver to Application server. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). ● Sravan:Complete Group service methods.
2013-06-16 | Prashanth,Sravan, Karthik | ● Prashanth: Fixed some quirks with Add Bill functionality (simple). ● Sravan: Created Group service methods (still need to test), Friends/Payments service methods. ● Karthik: Installed JBOSS AS. Began working on writing Hibernate config. | Complete AddBill (Simple, Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. Add MySQL driver to Application server. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). Complete Group service methods. | ● Prashanth: Complete AddBill (Simple, Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. ● Karthik: Install IDE, Glassfish. Setup basic dev environment. Study service & client. Add MySQL driver to Application server. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). Work with Prashanth to create normalized RDBMS data model● Sravan:Complete Group service methods.
2013-06-23 | Prashanth,Sravan, Karthik | ● Prashanth: Installed Xen VM box. Installed VPN, AS, MYSQL, Code servers and configured them appropriately. User setup. Data modelling with Karthik. ● Sravan: Created Friend, Payment record ● Karthik: Installed JBOSS on local machine. Studying DAO implementation (JPA + Hibernate) | Complete AddBill ( Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). | ● Prashanth: Complete AddBill (Simple, Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. ● Karthik: Study service & client. Add MySQL driver to Application server to your local machine. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). Work with Prashanth to create normalized RDBMS data model● Sravan: Install JBOSS server. Install MySQL server. Add MySQL driver to Application server to your local machine.
2013-06-30 | Prashanth, Karthik. Absent: Sravan - Sinus Problems | ● Prashanth, Karthik: Update the data model. Modified the Bill Classes accordingly. ● Sravan: | Complete AddBill ( Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). | ● Prashanth: Complete AddBill (Simple, Advanced, Equal Split, % split functionality) and create a basic JPA/Hibernate config. ● Karthik: Work on DAO impl, JPA/Hibernate Config. Work with Prashanth to create normalized RDBMS data model● Sravan: Install JBOSS server. Install MySQL server. Add MySQL driver to Application server to your local machine.
2013-07-07 | Prashanth. Absent: Karthik - Zions Park Vacation. Shravan - Travel to NJ | ● Prashanth: Wrote basic Hibernate/JPA config files with Spring. Completed upto 6 chapters of "Spring persistence with Hibernate". ● Sravan: ● Karthik: | Complete AddBill ( Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). | ● Prashanth: Complete AddBill (Simple, Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. ● Karthik: Study service & client. Add MySQL driver to Application server to your local machine. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). Work with Prashanth to create normalized RDBMS data model● Sravan: Install JBOSS server. Install MySQL server. Add MySQL driver to Application server to your local machine.
2013-07-14 | Absent: Prashanth - At Kamal's House. Shravan, Karthik | Prashanth: Updated Hibernate/JPA config files. Now the project is ready for querying the db. Sravan: Karhik: | Complete AddBill ( Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). | ● Prashanth: Complete AddBill (Simple, Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. ● Karthik: Study service & client. Add MySQL driver to Application server to your local machine. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). Work with Prashanth to create normalized RDBMS data model● Sravan: Install JBOSS server. Install MySQL server. Add MySQL driver to Application server to your local machine.
2013-07-21 | Prashanth, Sravan (Over phone) | Prashanth/Karthik: JPA config functional. Need to add more control and code DAO methods appropriately. Moving on to analyzing front-end Angular JS code. | Complete AddBill ( Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). | ● Prashanth: Complete AddBill (Simple, Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. ● Karthik: Study service & client. Add MySQL driver to Application server to your local machine. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). Work with Prashanth to create normalized RDBMS data model● Sravan: Install JBOSS server. Install MySQL server. Add MySQL driver to Application server to your local machine.
2013-07-28 | Prashanth, Sravan, Karthik | Prashanth/Karthik: No changes. Sravan: Understood most of Angular functionality. | Complete AddBill ( Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). | ● Prashanth: Complete AddBill (Simple, Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. ● Karthik: Study service & client. Add MySQL driver to Application server to your local machine. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). Work with Prashanth to create normalized RDBMS data model● Sravan: Install JBOSS server. Install MySQL server. Add MySQL driver to Application server to your local machine.
2013-07-28 | Prashanth, Sravan | Prashanth/Karthik: No changes. Sravan: Created "Add a New Group" page and working on adding the functionality to select group memberships etc. | Complete AddBill ( Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). | ● Prashanth: Complete AddBill (Simple, Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. ● Karthik: Study service & client. Add MySQL driver to Application server to your local machine. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). Work with Prashanth to create normalized RDBMS data model● Sravan: Continue work on adding Groups FUnctinality.
2013-08-04 | Prashanth, Sravan, Karthik | Sravan: Working on groups impl (Angular JS). Prashanth: Working on JPA DAO impl | Complete AddBill ( Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). | ● Prashanth: Complete AddBill (Simple, Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. ● Karthik: Study service & client. Add MySQL driver to Application server to your local machine. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). Work with Prashanth to create normalized RDBMS data model● Sravan: Continue work on adding Groups FUnctinality.
2013-08-11 | Prashanth, Sravan | Sravan: Working on groups impl (Angular JS). Prashanth: Working on JPA DAO impl | Complete AddBill ( Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). | ● Prashanth: Complete AddBill (Simple, Advanced, Equal Split, % split functionality) and display the added bill to the Bills json array. ● Karthik: Study service & client. Add MySQL driver to Application server to your local machine. Introduce hibernate to the project (maven dependencies, hibernate basic config, tying db details to hibernate config). Work with Prashanth to create normalized RDBMS data model● Sravan: Continue work on adding Groups FUnctinality.
2013-08-18 | Prashanth, Sravan | Sravan: Working on groups impl (Angular JS).CRUD on groups almost complete. Most of the impl done. Prashanth: Working on JPA DAO impl. JPA save,retrieve tested. Still have one pending issue on mapping. | Groups (Angular JS), Finializing JSON for the backend with JPA configuration completion. | Prashanth: Finalize JSON, complete JPA config (CRUD for bills). Sravan: Complete Groups CRUD on AngularJS (frontend). Karthik: Assist with JPA config.
2013-08-25 | Prashanth, Karthik (Sravan - Washington trip). Teja Kantamaneni volunteered to support. Assigned Spring security impl to him. | Prashanth, Jayanth Working on JPA impl. Introduced a JPA google code project to setup the JPA interfaces. Sravan: Working on groups CRUD on the frontend. | Improve JPA configuration. Get User object in totality. Solve transient (lazy/eager) issues for User object (user->group->users, user->friends->group->users etc. cyclic data calls!). Continue frontend work on Groups, AdvanceSplit. | Prashanth: JPA impl, Sravan: Groups, AdvanceSplit, Teja: Spring Security Impl /w Facebook impl.
2013-09-01 | Prashanth, Sravan. Karthik - Out of State. | Prashanth, Jayanth, Karthik: Got User object generated resolving most of cyclic data issues. JPA config improved with proper interface/impl configuration. Sravan: Working on Group CRUD, AdvanceSplit impl. | Resolve REST api, frontend CRUD impl (example - Bill CRUD json is different from that of the REST bill object). Impl AdvanceSplit. | Prashanth: REST api mistach. Figure out a strategy/plan/impl to resolve this. Sravan: AdvanceSplit impl. Teja: Spring Security Impl/Facebook. Karthik, Jayanth: Assist Prashanth to help with the impl.
2013-09-08 | Prashanth, Karthik, Sravan | Prashanth: Lazyloading/Eager and the data that needs to be pulled at login. Sravan: Groups on Frontende. | Restructure FrontEnd. Continue with FrontEnd impl for Groups, Bills | Prashanth: Restructure FrontEnd. Sravant: Groups on Frontend.
2013-09-15 | Prashanth, Abhishek, Sravan. | Prashanth: Restructuring the Client to separate out Ctrls,Svcs. Tying Backend to Frontend for Bills. Sravan: | Resolve Bill retrieval issues, fix AddBill(), Edit, DelBill by tying it to the Backend appropriately. Fix groups to work with the new structure. Move all Group related functinality to the GroupCtrl. | Prashanth: Resolve Bill retrieval issues, fix AddBill(), Edit, DelBill by tying it to the Backend appropriately. Sravan: Fix groups to work with the new structure. Move all Group related functinality to the GroupCtrl. Abhishek: Setup your workstation, Install git, Netbeans, JBOSS, MySQL.
2013-09-22 | Prashanth, Abhishek, Sravan. | Prashanth: Added Balances table, Domain Obj, Upgraded Spring to 3.2.4. Abhishek: Workstation setup complete. Sravan: Stuck with Office work. | Fix AddBill(), Edit, DelBill by tying it to the Backend appropriately. Fix groups to work with the new structure. Move all Group related functinality to the GroupCtrl. Complete Spring upgrade | Prashanth: Resolve Bill retrieval issues, fix AddBill(), Edit, DelBill by tying it to the Backend appropriately. Sravan: Fix groups to work with the new structure. Move all Group related functinality to the GroupCtrl. Abhishek: Study the Client & the Service
2013-09-29 | Prashanth, Abhishek, Sravan. | Prashanth:Tried and failed miserably to denormalize the backend (simpleuseridandliablecost). The same with Tomcat JNDI config. Abhishek: Studied the project. Sravan: Studied the service project. | Denormalize the service based on the forontend needs. Tomcat impl. Introduce Restangular to the Client. | Prashanth: Denormalization of service Sravan:Impl RestangularAbhishek: Tomcat Impl.
2013-10-06 | Prashanth, Abhishek, Sravan. | Prashanth:Tried and failed miserably to denormalize the backend (simpleuseridandliablecost). Helped Abhishek and Sravan with their tasks. Abhishek: Tomcat config complete with global JNDI datasource setting. Sravan: Restangular impl complete. | Denormalize the service based on the forontend needs. Begin Impl of Spring Security. Bill CRUD. | Prashanth: Denormalization of service Sravan:Impl Spring Security. Abhishek: Bill CRUD.
2013-10-06 | Prashanth, Abhishek, Sravan, Teja, Karthik. | Prashanth:Denormalization complete(simpleuseridandliablecost). Made addbill to rely on backend data instead of dummy data. Deprecated the dummy data. Abhishek: Helped Prashanth with addbill overhaul. Teja: Created Frontend security mechanism to show the login form by default and mock the auth. | Resolve addBill() issues (singleton/restangular/service issues). Proceed to fix edit/delete for Bills. Fix CRUD for Groups (rely on backend data). Add Groups drop down menu in bill List. Switching Groups should show the bills of that specific group. Create an exanded view for bill list. When user clicks on a bill it should show an expanded view of that bill showing all the details of the bill. Continue Security Implementation. | Prashanth: Resolve addBill() issues (singleton/restangular/service issues). Abhishek: Group CRUD. Karthik: Group dropdown, expanded bill view. Teja: Security, Sravan: restangular expansion
10/13,10/20 | updates are in Asana
2013-10-27 | Prashanth, Asbhishek, Sravan. Tasks are posted in Asana | Prashanth: Add, Delete done for Bills (End to End) Abhishek: Understanding on working on Groups CRUD. Sravan: Review of existing work | Continue Bill, Group CRUD updates, Expand Dashboard UI (Bill detailed view etc.) | Prashanth: Bills CRUD, Abhishek: Groups CRUD, Sravan: Dashboard UI expansion